## Project duration
Possible Scenarios Shakedown cruise --> Following assumption that can only two shakedown cruises can be failed
[12 empty] | Scenarios | Probability | Expected Duration
[11 empty] | 1 | Success on first try | 0.95 | 59.5
|  | Task Duration | Predecessors | Early | Early | Latest | Total |  |  |  | 2 | Fail ---> success | 0.0475 | 5.6525
No. | Task | (days) |  | Start | Finish | Finish | Slack |  |  |  | 3 | Fail ---> Fail | 0.0025 | 0.44625
1 | Secure funding (start) | 0 | - | 0 | 0 | -7.1054e-15 | -7.1054e-15
2 | Advertise | 14 | 1 | 0 | 14 | 14 | 0 |  |  | Weighted average Expected duration of project = |  |  |  | 65.5988 |  | 6.0988
3 | Purchase boats | 0 | 1 | 0 | 0 | 14 | 14 |  |  | up until end of shakedown cruise | [7 empty] | 112
4 | Make sails | 28 | 3 | 0 | 28 | 42 | 14
5 | Boat insurance | 7 | 3 | 0 | 7 | 42 | 35 |  |  |  |  | 3 months = |  | 91.26 | days
6 | Hire captains | 14 | 2,3 | 14 | 28 | 28 | 0 |  |  |  |  | 4 months = |  | 121.68 | days
7 | Hire Crewmembers | 14 | 2 | 14 | 28 | 41 | 13
8 | Hire Navigators | 14 | 6 | 28 | 42 | 42 | 0
9 | Stow supplies | 1 | 7 | 28 | 29 | 42 | 13 |  |  | Voyage to Asia | [5 empty] | Voyage back from Asia
10 | Shakedown Cruise | 17.5 | 4,5,8,9 | 42 | 59.5 | 59.5 | 0 |  |  | N~(91.26,78.95) | [5 empty] | N~(91.26, 45.10)
11 | Expected duration from failures | 6.1 | 10 | 59.5 | 65.6 | 65.6 | 0
12 | Shakedown end (milestone) | 0 | 11 | 65.6 | 65.6 | 65.6 | 0 |  | sigma = | 78.9473 |  |  |  |  | sigma = | 45.1008
13 | Buy Life insurance | 7 | 12 | 65.6 | 72.6 | 92.6731 | 20.0731
14 | Repairs, changes, restocks | 27.0731 | 12 | 65.6 | 92.6731 | 92.6731 | 0 |  |  | 95% Confidence interval | [5 empty] | 95% confidence interval
15 | Voyage to Asia | 91.26 | 13,14 | 92.6731 | 183.9331 | 183.9331 | 0 |  |  | LB | UB |  |  |  |  | LB | UB
16 | Voyage back to Spain | 91.26 | 15 | 183.9331 | 275.1931 | 275.1931 | 0 |  |  | -63.4767 | 245.9967 |  |  |  |  | 2.8625 | 179.6575
17 | End | 0 | 16 | 275.1931 | 275.1931 | 275.1931 | 0
[10 empty] | Duration = | [0, 246] |  |  |  |  | Duration = | [3, 180]
|  | Expected Project Duration = |  | 275.1931 | Days
[11 empty] | Project Duration Upper bound |  |  | 518.3273
[11 empty] | Project Duration Lower bound |  |  | 95.6731
182.52
| Costs | [9 empty] | 249.16
Your salary is for a salary of $270/day; Arturo Bayliner is paid $280/day while Juan de Puca is paid at $200/day;
| Classified ads currently cost $5000 per ad per week |  |  | 714.2857 | per ad per day
Captains are paid $310/day; navigators are paid $275/day and crewmembers are paid $80/day.
| Boat insurance premium (30% of each boat's cost) | [6 empty] | One time fee
Expected Cost of project up to Shakedown result (milestone) -- Based on ES - EF schedule
three
[5 empty] | three | Captain's | three | 125 | Boat |  | Boat
|  | My salary | Arturo Bayliner | Juan de Puca | Ads | Fees | Navigators | Crewmembers | Purchase | Sails | Insurance | Barebones | Hole foods
| daily Rate:: | 270 | 280 | 200 | 2142.8571 | 930 | 825 | 10000 | 137000 | 13700 | 41100 | 312.5 | 1250
[5 empty] | /3ads/day | [6 empty] | per SHAKEDOWN CRUISE day (for combined crew)
| Total Number of Days | 59.5 | 59.5 | 59.5 | 14 | 31.5 | 17.5 | 31.5 | - | - | - | 17.5 | 17.5
Total Cost |  | 16065 | 16660 | 11900 | 30000 | 29295 | 14437.5 | 315000 | 137000 | 13700 | 41100 | 5468.75 | 21875
[12 empty] | Scenarios |  |  |  |  | Probabilities
[11 empty] | 1 | Success on first try |  | 652501.25 | Subtotal scenario 1 |  | 0.95
[11 empty] | 2 | Fail ---> success |  | 1158906.6667 | Subtotal scenario 2 |  | 0.0475
[11 empty] | 3 | Fail ---> Fail |  | 1665312.0833 | Subtotal scenario 3 |  | 0.0025 | 59211.3469
[14 empty] | 679087.5344 | Weighted avg E[Cost] of project up to Shakedown result
E[Cost] of final preparations for final voyage (restock of food, life insurance)
[8 empty] | Captain | [9 empty] | Total food cost
[8 empty] | Life insurance | Barebones | Hole foods | [7 empty] | 312531.25
| daily Rate:: | [6 empty] | 102371.838 | 312.5 | 1250
Per VOYAGE DAY (for combined crew)
| Total Number of Days | [6 empty] | - | 182.52 | 182.52
[8 empty] | 102344.64 | 57037.5 | 228150 |  |  |  | 387532.14 | E[Cost] of final preparations for final voyage (restock of food, life insurance, salaries before voyage begins)
E[Cost] of salaries payable after the shakedown cruise and during final voyage
three
[5 empty] | Captain's | three | 125
|  | My salary | Arturo Bayliner | Juan de Puca | Fees | Navigators | Crewmembers
| daily Rate:: | 270 | 280 | 200 | 930 | 825 | 10000
| Total Number of days | 209.5931 | 209.52 | 209.52 | 209.52 | 209.52 | 209.52
|  | 56590.1405 | 58665.6 | 41904 | 194853.6 | 172854 | 2095200 | [6 empty] | 2620067.3405 | E[Cost] of project of final voyage
[14 empty] | 3686687.0149 | E[Cost] of Entire project
Key costs
|  | Administrative |  |  | Captains | Navigators | Crew | Boat (inclusive of purchase cost, sails, insurance) | Captain's life | Barebones | Hole foods
|  | 201784.7405 |  |  | 224148.6 | 187291.5 | 2410200 |  | insurance | food expenditure | expenditure
[8 empty] | 191800 | 102344.64 | 62506.25 | 250025

## boat decision
|  |  | probability of | Two -way |  |  |  | Total | Cargo
Decision |  |  | sucessfully reaching | prob of | Purchase | Cost | Crew | Crew | capacity | Cargo | Total | Costs | Capacity |  | Assuming crew pay will occur over expected 6 month duration
Y/N | Boat | type boat | asia | success | cost | Sails | size | Cost | (kg) | Cost | cost | (Chosen) | (chosen) |  | (30days per month on avg)
0 | 1 | Schooner | 0.8 | 0.64 | 40000 | 4000 | 26 | 479700 | 1000 | 58500 | 582200 | 0 | 0
1 | 2 | Carrack | 0.95 | 0.9025 | 55000 | 5500 | 40 | 681300 | 1200 | 90000 | 831800 | 831800 | 1200
0 | 3 | Caravel | 0.7 | 0.49 | 30000 | 3000 | 30 | 537300 | 1050 | 67500 | 637800 | 0 | 0 |  |  | Captain total cost during final voyage
1 | 4 | Carrack | 0.9 | 0.81 | 42000 | 4200 | 40 | 681300 | 1200 | 90000 | 817500 | 817500 | 1200 |  |  | 55800
0 | 5 | Caravel | 0.3 | 0.09 | 17500 | 1750 | 25 | 465300 | 1250 | 56250 | 540800 | 0 | 0
1 | 6 | Schooner | 0.85 | 0.7225 | 40000 | 4000 | 45 | 753300 | 1450 | 101250 | 898550 | 898550 | 1450 |  |  | Navigator total cost during final voyage
[5 empty] | 137000 | 13700 | 125 | 2115900 |  | 281250 | [5 empty] | 49500
# of Ships Constrant |  |  |  | Two-way Success Constraint | [8 empty] | Capacity Constraint
3 | == | 3 |  | 0.81167 | >= | 0.8 | [6 empty] | 3850 | >= | 3500 | Cargo Cost
[16 empty] | 5 | per day per crew member | 62.5
[16 empty] | 20 | per day per crew member
capacity Used
[16 empty] | 312.5 | per day for bare bones | 0.05 | kg per day
Total Cost
DON’T CHANGE BLUE CELLS | [11 empty] | 2547850 |  |  |  | 1250 | per day for hole foods | 0.08 | kg per day
56250
225000
182.52

## simulation for repair task
Monte-Carlo Simulation for Repair task
Beta Distribution
|  |  |  | Duration Estimates |  | Expected |  |  |  | Random
Task | Description | Predecessors | Optimistic | Pessimistic | Most likely | Duration | Variance | Alpha | Beta | Seed
14 | Repairs, changes, restocks | 12 | 7 | 56 | 24.5 | 26.8333 | 66.6944 | 3.1059 | 4.5675 | 0.16383
Task Duration
Task | (Beta Distribution)
14 | 18.3886
Trial No. | Task Duration
1 | 18.3886
2 | 22.6024
3 | 26.7491
4 | 38.6376
5 | 29.5
6 | 18.2986
7 | 34.5246
8 | 25.4462
9 | 20.5007
10 | 32.9163
11 | 32.6684
12 | 27.8977
13 | 22.1786
14 | 31.9878
15 | 44.738
16 | 27.8988
17 | 12.6495
18 | 27.7071
19 | 29.0163
20 | 31.2625
21 | 26.1899
22 | 45.7842
23 | 34.9416
24 | 44.1435
25 | 32.6718
26 | 23.0415
27 | 33.1397
28 | 25.1158
29 | 20.4217
30 | 20.734
31 | 21.2411
32 | 32.8209
33 | 21.6658
34 | 18.116
35 | 20.6762
36 | 34.2787
37 | 28.837
38 | 25.7221
39 | 43.6144
40 | 16.0197
41 | 15.443
42 | 20.0435
43 | 9.6692
44 | 25.9629
45 | 38.027
46 | 15.0002
47 | 21.0689
48 | 28.3847
49 | 16.6864
50 | 25.1942
51 | 12.8936
52 | 23.1871
53 | 22.8726
54 | 31.7658
55 | 15.0013
56 | 40.3774
57 | 23.5385
58 | 44.5821
59 | 28.1938
60 | 24.2119
61 | 21.217
62 | 31.9957
63 | 14.5911
64 | 42.3134
65 | 23.6789
66 | 37.0802
67 | 31.4985
68 | 40.742
69 | 39.5464
70 | 12.1681
71 | 21.4965
72 | 42.7568
73 | 26.0525
74 | 36.2639
75 | 38.9191
76 | 30.9969
77 | 20.0747
78 | 29.078
79 | 41.2548
80 | 27.5542
81 | 29.1667
82 | 11.6249
83 | 26.2828
84 | 26.9272
85 | 31.3111
86 | 27.6208
87 | 20.4219
88 | 17.7601
89 | 24.1214
90 | 34.2588
91 | 23.653
92 | 20.6657
93 | 16.1565
94 | 26.9343
95 | 26.7949
96 | 34.2325
97 | 46.4123
98 | 14.2515
99 | 43.5302
100 | 28.4955
101 | 27.7414
102 | 24.0615
103 | 30.1283
104 | 32.0545
105 | 30.171
106 | 25.0437
107 | 31.6529
108 | 28.8498
109 | 21.5264
110 | 25.6272
111 | 37.4058
112 | 43.0075
113 | 31.925
114 | 12.2022
115 | 27.3429
116 | 27.7604
117 | 41.6944
118 | 36.0108
119 | 39.0918
120 | 32.2941
121 | 35.0565
122 | 29.4627
123 | 24.2685
124 | 19.8114
125 | 24.2533
126 | 27.7961
127 | 24.7307
128 | 14.9627
129 | 27.5957
130 | 23.897
131 | 28.5641
132 | 19.9809
133 | 11.4542
134 | 32.1078
135 | 14.8258
136 | 24.3006
137 | 26.0954
138 | 36.0483
139 | 30.1856
140 | 34.5947
141 | 24.2861
142 | 23.9891
143 | 30.8327
144 | 27.4537
145 | 40.7985
146 | 27.2702
147 | 17.0432
148 | 37.3285
149 | 24.7241
150 | 14.4628
151 | 26.0938
152 | 43.0913
153 | 36.9148
154 | 28.4032
155 | 35.8982
156 | 29.848
157 | 32.0635
158 | 17.6286
159 | 16.7022
160 | 41.353
161 | 28.0074
162 | 27.1588
163 | 17.8242
164 | 32.5727
165 | 32.55
166 | 23.8446
167 | 34.0086
168 | 24.2326
169 | 24.8341
170 | 22.4046
171 | 29.4207
172 | 12.3684
173 | 21.3837
174 | 23.7936
175 | 17.0805
176 | 13.4086
177 | 17.0991
178 | 38.3633
179 | 33.4601
180 | 35.1881
181 | 40.3694
182 | 26.1251
183 | 13.2451
184 | 35.0147
185 | 18.4852
186 | 32.7723
187 | 12.9224
188 | 30.8315
189 | 13.9948
190 | 39.2625
191 | 32.6629
192 | 30.3189
193 | 30.9374
194 | 29.1267
195 | 35.4029
196 | 32.7671
197 | 22.4216
198 | 37.4928
199 | 39.9824
200 | 23.2546
201 | 37.6658
202 | 23.712
203 | 21.6511
204 | 26.7469
205 | 23.1263
206 | 12.8866
207 | 24.378
208 | 19.1322
209 | 32.3646
210 | 20.3054
211 | 19.8696
212 | 24.4553
213 | 35.7437
214 | 21.5643
215 | 25.6719
216 | 10.4136
217 | 34.9666
218 | 24.0003
219 | 42.0064
220 | 21.2388
221 | 24.9966
222 | 40.3865
223 | 26.7909
224 | 33.0768
225 | 45.4497
226 | 15.0004
227 | 30.8347
228 | 30.9166
229 | 18.1827
230 | 45.7396
231 | 20.8629
232 | 25.913
233 | 21.3726
234 | 24.3213
235 | 41.5742
236 | 32.6508
237 | 44.6527
238 | 10.9785
239 | 27.7325
240 | 13.2523
241 | 18.8417
242 | 36.2963
243 | 24.2412
244 | 12.3567
245 | 18.0751
246 | 47.4698
247 | 21.5503
248 | 24.5291
249 | 18.3254
250 | 22.2406
251 | 29.9113
252 | 33.206
253 | 38.4173
254 | 37.0754
255 | 37.4345
256 | 17.6324
257 | 34.2122
258 | 31.5557
259 | 40.1114
260 | 29.664
261 | 16.1106
262 | 13.3788
263 | 30.5384
264 | 27.7241
265 | 38.5408
266 | 13.2252
267 | 28.3626
268 | 24.3988
269 | 28.4663
270 | 15.8217
271 | 18.7856
272 | 11.1506
273 | 25.4031
274 | 22.3835
275 | 22.7029
276 | 25.1929
277 | 39.2816
278 | 26.4282
279 | 24.0827
280 | 31.6412
281 | 35.1872
282 | 18.5171
283 | 30.165
284 | 45.0821
285 | 24.9086
286 | 28.2501
287 | 27.3134
288 | 28.5784
289 | 20.493
290 | 14.928
291 | 32.4563
292 | 27.4127
293 | 18.9209
294 | 10.0434
295 | 29.8257
296 | 24.5579
297 | 15.9863
298 | 25.302
299 | 33.7045
300 | 13.5695
301 | 24.7174
302 | 20.9823
303 | 32.3574
304 | 23.3097
305 | 26.2397
306 | 31.5383
307 | 26.1068
308 | 29.8519
309 | 9.5121
310 | 18.8943
311 | 42.9509
312 | 31.3494
313 | 20.153
314 | 20.7608
315 | 15.6608
316 | 23.5589
317 | 20.4293
318 | 33.6789
319 | 17.3414
320 | 21.963
321 | 25.3738
322 | 21.6742
323 | 13.638
324 | 41.0273
325 | 15.8562
326 | 30.5608
327 | 21.1369
328 | 33.0778
329 | 16.8377
330 | 37.4917
331 | 34.431
332 | 23.4166
333 | 33.7592
334 | 25.8069
335 | 32.5985
336 | 17.5227
337 | 23.0264
338 | 25.0058
339 | 23.8498
340 | 22.7081
341 | 23.1377
342 | 38.3652
343 | 11.6259
344 | 20.1439
345 | 14.4961
346 | 31.1328
347 | 25.3066
348 | 27.7649
349 | 30.6063
350 | 36.5253
351 | 24.0817
352 | 34.0811
353 | 51.1935
354 | 24.9719
355 | 20.9187
356 | 26.2835
357 | 28.2266
358 | 22.3957
359 | 17.2467
360 | 34.8504
361 | 17.009
362 | 15.7892
363 | 23.6921
364 | 31.09
365 | 17.9052
366 | 23.9769
367 | 27.404
368 | 29.385
369 | 26.6867
370 | 29.3903
371 | 31.8998
372 | 41.5623
373 | 32.8425
374 | 13.0591
375 | 17.4969
376 | 37.6719
377 | 18.8237
378 | 23.044
379 | 36.5963
380 | 28.7903
381 | 41.8982
382 | 32.5536
383 | 29.4377
384 | 46.6394
385 | 23.8953
386 | 17.513
387 | 21.122
388 | 16.2252
389 | 33.0823
390 | 31.7783
391 | 32.3623
392 | 19.4533
393 | 16.8831
394 | 23.3136
395 | 23.4876
396 | 31.0677
397 | 39.0737
398 | 36.4485
399 | 31.9736
400 | 39.9453
Average Duration | 27.0731